## Roadmap Capacity
Quarter | Workstream | Primary Outcomes | Engineering Allocation | Key Dependencies | Exit Criteria | Risks | Mitigations
Q1 | MVP foundations | Telemetry contract; ingestion adapter; stream processor skeleton; alert store; core APIs; initial UI | 4 BE + 2 FE + 1 QA + 1 Tech Lead | Ingestion Gateway contract; product UX decisions | Synthetic stream processed end-to-end; top 4 anomaly types implemented; dashboard behind feature flag | Gateway delay; scope creep | Versioned adapter; synthetic telemetry; strict MVP anomaly catalog
Q1 | Operational readiness | SLO dashboards; synthetic health events; runbooks; load-test harness | 1 BE + 1 QA | Observability stack; platform SRE review | Processing freshness and API latency visible; Sev-1 runbook reviewed | Reliability deferred until late | Make observability an MVP gate
Q1 | Legacy offline stabilization | Instrument heartbeat service; identify false-offline root causes; ship narrow patch | 2 BE + QA support | Support ticket samples; customer impact data | Support escalations trending down; root causes documented as Health Center test cases | Interrupt work expands indefinitely | Two-to-three-week stabilization lane with explicit exit criteria
Q2 | GA hardening | Replay/backfill; idempotency; alert lifecycle; suppression; richer drill-down; tenant expansion | 5 BE + 2 FE + 2 QA + 1 Tech Lead | MVP production telemetry; scale-test environment | GA readiness review passed; phased tenant rollout approved | Data correctness defects under scale | Load tests; replay tests; shadow validation
Q2 | Legacy migration validation | Shadow compare Health Center offline status against legacy heartbeat | 2 BE + 1 QA | Legacy service data; Health Center event coverage | False-positive and false-negative rates understood; migration plan approved | Premature source-of-truth switch | Dual-read validation; tenant allowlist migration
Q3 | Platformization | Reusable coalescing framework; expanded rule catalog; historical trends; notification hooks | 4 BE + 2 FE + 2 QA | GA feedback; notification platform alignment | Reusable APIs documented; at least one additional platform use case onboarded | Generic platform overbuild | Evolve from proven MVP patterns only
Q3 | Legacy reduction | Move selected offline decisions to Health Center; retire duplicated legacy paths where safe | 3 BE + 1 QA | Migration validation; customer rollout approvals | Reduced support burden; decommission plan for replaced legacy logic | Customer-visible regression | Progressive rollout; rollback; freshness indicators